## backlog
User stories | Tasks | Status
I, as data engineer, retrieve, explore and analyze the dataset | Explore the content of JSON file | Done
| Analyze the different columns | Done
I, as data engineer, clean and preprocess the data | Remove rows with NaN values | Done
| Remove inconsistent values (for example 'not relevant') | Done
| Select the columns for our case and set the appropriate type | Done
| Create feature columns for clustering | Done
I, as data engineer, create clustering model | Use Jupyter for a fastforward execution | Done
| Use Kmeans algorithme from ML Spark | Done
| Use Pyspark to make the code conversion easier | Done
I, as data engineer, industrialize the clustering model on Spark Cluster | Convert from ipynb to py file | Done
| Submit the py file and ressources on Spark | Done
| Test the local execution on a personal Spark Cluster | Done
We, as data engineer and datascientist, test on a pre-production Spark Cluster | Ensure PySpark installed on all nodes | To do
| Submit the code and ressources accross the cluster | To do
| Check the Spark UI for Running applications | To do
| Test the results | To do
I, as data engineer, industrialize using a container | Configure the container: pyspark and all dependencies | To do
| Configure Spark drivers and ports | To do
| Run the container | To do